## Sheet1
EduTrack Website
Task No. | Task Name | Description | Owner | Start Date | End Date | Duration | Priority | Status | Remark
1 | Information Gathering | Define Feature | Project Manger | 2026-05-01 | 2026-05-03 | 3 days | High
2 | UI design | Create a Layout | Designer | 2026-05-04 | 2026-05-08 | 5 days | High
3 | Front End Developer | Build UI pages | Developer | 2026-05-09 | 2026-05-18 | 10 days | High
4 | Back End Developer | Database and coding | Developer | 2026-05-09 | 2026-05-20 | 12 days | High
5 | Testing | Bug Fixing | Tester | 2026-05-21 | 2026-05-25 | 5 days | Medium
6 | Deployment | Launch Website | Team | 2026-05-26 | 2026-05-28 | 2 days | High